## README
Chaos Engineering Scenario Catalog
Audience: Sr. technical leadership (program review) and the Chaos Engineering team (execution). Derived from code-based assessment artifacts, C1–C4/EAC diagrams, the recon (DTR) pipeline diagram/narrative, and prior FMEA / timeout-chain / DR work. Nothing in the catalog is invented beyond those sources; unknowns are flagged in Open Items.
Sheets
1. Service Inventory | The 17 Core services with archetype, DR posture, ingress, data stores, RDS Proxy status, dependencies and scheduled jobs. Source of truth for scenario targeting.
2. Scenario Catalog | The full experiment catalog. One row per scenario. Filter by Wave, Fault Domain, Archetype, Target Service or Injection Plane.
3. Priority Model | Scoring definitions for Likelihood and Severity, and how Priority and Wave assignment work.
4. Wave Plan | Execution waves with theme, entry/exit criteria and live scenario counts.
5. Coverage Matrix | Fault Domain × Wave and Fault Domain × Injection Plane counts, computed live from the catalog.
6. Open Items | Unknowns, confirmations pending, and documentation gaps that gate specific scenarios.
7. App Scan Instructions | Durable method for scanning any application repo (Maven multi-module) for resilience-relevant facts: dependency/version census, resilience config, timeout chain, retry amplification inputs, Kafka consumer config, idempotency evidence, anti-pattern sweep, and perf-vs-prod profile diff. Re-runnable on future services unchanged.
8. Infra Scan Instructions | Durable method for discovering cloud components from infrastructure-as-code (tool-agnostic: Terraform/CDK/CloudFormation/Serverless), reconciling them against the Service Inventory tab, and onboarding new AWS components/services into the taxonomy going forward.
Key concepts
Injection plane | Infrastructure = fault injected below the app (FIS, network, AWS resources). Application = fault injected inside the request path (latency/exceptions/errors via app-level tooling or a proxy). Compound = multiple simultaneous faults. Detection = the hypothesis is about observability, not recovery.
Dual success criteria | Every scenario has TWO pass conditions: the system behaved as hypothesized AND the fault was detected/alerted correctly (Dynatrace + CloudWatch). A fault that recovers silently is a FAILED experiment. Detection baseline scenarios (CE-OBS-*) run in Wave 1 for this reason.
PERF validity | High = result transfers to PROD with confidence. Medium = transfers with caveats (capacity/data-volume/config deltas). Low = PERF result is indicative only; needs eventual PROD validation or explicit delta analysis.
Steady state first | A scenario is not runnable until its steady-state signal exists and is trusted. If the SLI/dashboard for the hypothesis is missing or unvalidated, that is itself a Wave-1 finding.
How to use (chaos team)
Cells to fill in | YELLOW cells are yours to populate: FMEA Ref (map each scenario to the existing FMEA scenario IDs — ASSESSED items first), Journeys (which of the 16 official journeys the scenario exercises), and Status as work progresses (Proposed → Ready → Executed → Confirmed / Finding).
Example of a filled row | CE-COM-01 carries example values in its FMEA Ref and Journeys cells (marked 'EXAMPLE —') showing the expected format. Replace with real IDs.
Prerequisites | Prereq IDs = scenarios that must be Confirmed before this one is meaningful (singles before compounds). Waves are sequenced so prerequisites always land in an earlier or same wave.
Governance | Wave 1–2 run in PERF game days with evidence capture per run. Wave 3–4 include coordination-heavy and DR drills; treat each as a scheduled event with stakeholder sign-off. Production experimentation is out of scope for this catalog version.

## Service Inventory
# | Service | Acronym | APG | Archetype | DR Posture | Ingress | Data Stores | RDS Proxy | Core-internal Sync Deps | External Sync Deps | Async Produces / Consumes | Scheduled Jobs | Doc Status / Notes
1 | Account Locator Component | ALS | LOCR | Sync API + batch extract — mixed | Active/Active (latency routing) | R53→NLB→API GW→NLB→ALB→ECS | Aurora (direct), ElastiCache, S3 (RDS→S3 Lambda) | No (direct) | ACL (Register) | Inbound only (ARR/FAP/DCPA/DCP/Payments/SPG/OCS) | Prod: Locator Event→MBUS→Datalake; Batch: Lambda→S3→MFT→EDX | Batch extract | OK
2 | Account Reference Management | ARM | ACCT | Sync API | Active/Active | R53→NLB→API GW→NLB→ALB→ECS | Aurora (direct), ElastiCache | No (direct) | Inbound only (SAM/AFM/DBE/DTE/DSM/DCM) | none | none shown | none | OK
3 | Core Account Management | SAM | ACCT | Orchestrator (acct lifecycle) — mixed | Active/Passive | R53→NLB→API GW→NLB→ALB→ECS (from SMB/ARR) | Aurora (direct — Core DB) | No (direct) | ALS, ARM, AFM, ACL | CBS (Account Mgmt) | Prod: Core Acct Change→MBUS→Datalake; Cons: MBUS incl. RECN EOD Completion | none | OK
4 | Account Feature Management | AFM | ACCT | Sync API + event publisher — mixed | Active/Passive | R53→NLB→API GW→NLB→ALB→ECS (from SAM) | Aurora (direct — AFM DB), ElastiCache | No (direct) | MCC, DBE, DSM, DCM, ARM, ACL | CBS Posting, CBS Transaction | Prod: Feature State Change→MBUS (→DCP-TA, Datalake) | none | OK
5 | Account Locator Admin Tool | DLAT | LOCR | Not shown (infra diagram only) | Active/Passive (per rule) | R53→NLB→ALB→ECS — NO API GW | Aurora (direct), S3 | No (direct) | not shown | not shown | not shown | none | GAP — dependencies undocumented
6 | Attribute Change Log | ACL | ACCT | Event aggregator/consumer + Sync API — mixed | Active/Passive (per rule) | R53→NLB→API GW→NLB→ALB→ECS | Aurora (direct — History Datastore) | No (direct) | Receives SAM/AFM/ALS registrations | none | Cons: Core Acct Change, Feature Change (SAM/AFM/ALS) | none | OK
7 | Core Subledger Management | DSM | REFD | Sync API + event publisher — mixed | Active/Passive; cross-region repl., bidirectional Aurora | External NLB→API GW→Internal NLB→ALB→ECS Anywhere | Aurora (direct — writer/reader nodes), IN-MEMORY HASHMAP | No (direct) | MCC, ARM (migration lookup) | CBS (Subledger+RoutingRule, Balance Inquiry), Payments/MMS | Prod: Subledger CUD→MBUS→AU+Continuum/DataLake; +Migration Topic | none | In-memory state — see CE-COM-05
8 | Spend-Track Experience Svc | SSE | REFD | No diagram provided | 3-Active (+us-west-2, stateless per rule) | no diagram | no diagram | TBC | no diagram | no diagram | no diagram | none | GAP — no artifact at all; scenarios blocked
9 | Tasks Experience Svc | CHE | ENRC | Edge/BFF | 3-Active (+us-west-2, stateless) | Via DPS Proxy/Digital; shares 900069 ingress | none of its own shown | n/a | DCM (Task Inquiry for Nudges), MCC (Spend Categories) | none shown | none shown | none | Reconstructed from other diagrams
10 | Transaction Experience Svc | TE | ALRT | Edge/BFF | 3-Active (+us-west-2) | Akamai→CTC→DPS Proxy→Transit GW→R53→API GW (AuthAnywhere token validate)→NLB→ALB→ECS | none (stateless) | n/a | none | ChannelContext, ETU/TU Transactions, GKP on-prem via Envoy, AuthAnywhere | none shown | none | OK
11 | MCC Data Management Svc | MCC | REFD | Sync API (ref data) + scheduled pipeline — mixed | Active/Passive; DR: PILOT LIGHT | API GW→NLB→ALB→ECS (+ On-Prem API GW); EventBridge scheduler (ETU pull) | Aurora (direct — Local Data Store), S3 (config) | No (direct) | Inbound only (DSM, SAM/Acct Creation, Tasks Exp) | ETU (GET Reference Data, scheduled) | Scheduler-triggered ETU pull; writes config→S3; no Kafka publish | EventBridge ETU pull | OK
12 | Core Task Management | DCM | ENRC | Sync API (CRUD) + event publisher + scheduled job — mixed | Active/Passive (Warm Standby) | Via DPS Proxy/Digital & Banking Payments→NLB→NLB→ALB (+API GW Regional Endpt); weekly-job scheduler via SQS | Aurora (RDS PROXY, separate Global cluster), ElastiCache (shared), SQS+DLQ | YES | ARM, SAM, Core Alerts (DCC 900070) | CBS (posting/balance inquiry via Digital Payments) | Prod: Task Life Cycle→MBUS (→Alerts, DTE); SQS: weekly future-task job | Weekly SQS-driven job | OK
13 | Core Balance Enrichment | DBE | ENRC | Event processor + Data-Quality/Balances API — mixed | Active/Passive (Warm Standby; RTO<2h, RPO PoF) | Kafka (MBUS) CBS Balance Changed; + API (API GW→NLB→ALB) | Aurora (RDS PROXY, shared Global cluster/own schema), ElastiCache (shared) | YES | ARM (acct identifier), DSM (Subledger Inquiry — cache-miss fallback) | none | Cons: CBS Balance Changed. Prod: Enriched Sub-Ledger Balance Updated→MBUS→AU | none | Parameter Store reload strategy
14 | Core Transaction Enrichment | DTE | ENRC | Event processor + Data-Quality/Subledger-Txn API — mixed | Active/Passive (Warm Standby) | Kafka (MBUS) CBS Transaction Events; + API (API GW→NLB→ALB) | Aurora (RDS PROXY, shared Global cluster/own schema), ElastiCache (shared) | YES | ARM, DSM (fallback), Task Svc (Get Task Name) | none | Cons: CBS Transaction Events. Prod: Enriched Sub-Ledger Txn→MBUS→ETU | none | Drawn from shared PDF (folders 13/15)
15 | Core Sub Ledger Data Consumer | DSC | ENRC | Event processor (consumer → cache warmer) | Active/Passive (Warm Standby) | Kafka (MBUS) Subledger CUD / Partition Lifecycle (from DSM) | ElastiCache (writes subledger type/name), Aurora (shared cluster/own schema) | No (direct) | none | none | Cons: Subledger CUD/Lifecycle. Prod: none | none | Cache-warmer — silent-failure risk
16 | Core Transaction Recon | DTR | RECN | Recon / pipeline (batch + event-driven) | Active/Passive; cross-region S3 + bidirectional Aurora | file/MFT (EDX RDF/ADF/CDF→S3→SQS→Lambda); EventBridge scheduler; Kafka CBS EOD Completion | S3 (recon/ack/anomaly), ElastiCache (EOD txn cache), Aurora Global, SQS | No (direct) | Core Transaction Svc (Txn Inquiry — SOR fallback) | CBS (EOD Txn Inquiry, Posting API for corrections), EDX (email) | Cons: CBS EOD Completion + Balance/Txn CUD. Prod: Bankwise Recon Completion→Acct Closure (SAM), Recon Event; SQS/SNS/Lambda | EventBridge SLA validator | Dual-trigger pipeline — see CE-PIPE
17 | Core Alerts | DAL | ALRT | Event processor + API intake — mixed | Active/Passive | Kafka (Enriched Txn CUD, Task Lifecycle, D2 Alert Topic) + API; CRON scheduler (failure recovery); API GW/NLB/ALB/R53 | Aurora (direct — Alerts DB / RDS Global) | No (direct) | none | CSU (Fetch Parent/Child, payload enrichment) | Cons: Enriched Txn CUD + Task Lifecycle. Prod: enriched alerts→Notify Alert Topic→NOTIFY | Cron (failure recovery) | OK

## Scenario Catalog
ID | Scenario | Fault Domain | Injection Plane | Archetype(s) | Target Service(s) | Fault / Injection | Hypothesis (steady state holds if…) | Tooling / Method | Blast Radius | Abort Condition | Success — System | Success — Detection | PERF Validity | PERF Note | Likelihood (1-5) | Severity (1-5) | Priority | Wave | Prereq IDs | FMEA Ref (FILL) | Journeys (FILL) | Status | Likelihood Tier | Risk Rating
CE-COM-01 | Single Fargate task termination — sync API | Compute | Infrastructure | Sync API | SAM (repeat per sync API) | Terminate 1 running task of the service under steady synthetic load. | ECS replaces the task; ALB deregisters/drains; journey SLI stays within SLO; zero 5xx beyond in-flight requests. | FIS aws:ecs:stop-task | Single task | SLI breach > 2 min | Task replaced ≤ target time; no request loss beyond in-flight; connection re-establishment clean. | Dynatrace detects task churn; no false-positive paging for single-task events (noise calibration). | High | Recovery mechanics transfer; scaled-down task counts change % impact only. | 4 | 2 |  | 1 |  | EXAMPLE — FMEA-ECS-004, FMEA-ECS-011 | EXAMPLE — J03, J07 | Proposed
CE-COM-02 | Bulk task termination (50%) under load | Compute | Infrastructure | Sync API | ARM, SAM | Terminate 50% of tasks simultaneously under load. | Remaining tasks absorb load without pool/thread exhaustion; scale-out restores capacity; SLI degrades within tolerated bounds. | FIS aws:ecs:stop-task (percentage) | One service | Error rate >5% for >3 min | No cascading failure to callers; scale-out completes; queuing recovers. | Capacity alarm fires; Dynatrace shows saturation before errors. | Medium | PERF task counts/scaling policies differ from PROD — % result indicative only. | 3 | 3 |  | 1 | CE-COM-01 |  |  | Proposed
CE-COM-03 | Task kill during rolling deployment | Compute | Infrastructure | Sync API | One sync API | Inject task termination while a deployment is replacing tasks. | Deployment circuit breaker / min-healthy settings prevent capacity dropping below safe floor; rollback triggers if needed. | FIS + pipeline coordination | One service | Healthy count < min for >2 min | No dual-capacity loss; deploy completes or rolls back cleanly. | Deploy-time alerting distinguishes deployment churn from failure. | High | Deployment config parity assumed — verify. | 3 | 3 |  | 2 | CE-COM-01 |  |  | Proposed
CE-COM-04 | Event-processor task kill mid-consumption | Compute | Infrastructure | Event processor | DBE, DTE | Kill a consumer task while it processes a batch of CBS events. | Offsets uncommitted messages are redelivered; enrichment is idempotent — no lost and no duplicate enriched events downstream (AU/ETU). | FIS aws:ecs:stop-task | One consumer group member | Consumer lag > threshold, no drain | Rebalance completes; redelivered messages produce identical enriched output exactly once (effective). | Lag + rebalance visible in Dynatrace; DLQ/poison alarms silent. | High | Idempotency logic is environment-independent. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-COM-05 | DSM task recycle — in-memory hashmap loss | Compute | Infrastructure | Sync API (stateful) | DSM (+DSC warmer) | Recycle DSM tasks; measure window where in-memory subledger map is cold before DSC/ElastiCache warm state is usable. | DSM serves correct responses during warm-up (falls back to Aurora/ElastiCache) with bounded latency penalty; no wrong answers from empty map. | FIS aws:ecs:stop-task | DSM only | Incorrect subledger responses | Zero correctness violations; warm-up window quantified; fallback path exercised. | Warm-up window observable as metric; DSC warmer health alarmed. | High | Pattern risk is design-level, not capacity-level. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-COM-06 | ECR image pull failure during scale-out | Compute | Infrastructure | Any | One sync API | Block image pulls (registry deny / endpoint block in PERF) then force scale-out. | Existing tasks keep serving; scale-out failure is alarmed; no flapping replacement loop kills healthy capacity. | Custom (endpoint/registry policy) | One service | Healthy capacity shrinking | Steady state maintained on existing tasks; clear failure signal. | Scale-out failure alarm exists and fires (suspected gap). | High | — | 2 | 3 |  | 2 |  |  |  | Proposed
CE-COM-07 | Memory pressure → container OOM behavior | Resource | Application | Sync API | One JVM service | Drive heap growth via app-level memory assault until container limit. | OOM kill is clean (task replaced) rather than gray degradation; no long GC-driven brownout serving errors. | App-level (Chaos Monkey for Spring Boot / stress endpoint) | One task | SLI breach | Fail-fast behavior; replacement clean; heap/GC limits tuned. | GC/heap alerting catches degradation BEFORE OOM. | High | JVM behavior transfers. | 3 | 3 |  | 2 | CE-COM-01 |  |  | Proposed
CE-COM-08 | Scheduled-job duplicate / missed execution | Compute | Application | Scheduled job | DCM weekly job, MCC ETU pull, DAL cron | Run service at >1 task through a scheduled window; separately kill task at trigger time. | Job fires exactly once per window (locking/leader election proven); a missed window is detected and recovered per design. | Scale/kill + job observation | Job outputs | Duplicate side-effects detected | No duplicate task-job effects / double ETU pull / double alert recovery; missed-window path defined. | Missed or duplicate execution alarms (suspected gap for all three). | High | Logic-level, environment-independent. | 3 | 4 |  | 1 |  |  |  | Proposed
CE-DB-01 | Aurora writer failover — RDS-Proxy-fronted | Data-Aurora | Infrastructure | Mixed (ENRC) | DCM, DBE, DTE | Trigger in-region writer failover on the proxy-fronted cluster under load. | RDS Proxy preserves/pins client connections; app-visible impact limited to brief write latency; no connection storm. | FIS aws:rds / failover-db-cluster | ENRC cluster | Error rate >5% / 3 min | Failover ≤ target; HikariCP pools stable; writes resume without app restarts. | DB failover event alarmed; Dynatrace DB-layer signal correct. | Medium | Instance class + data volume affect failover duration. | 3 | 4 |  | 1 |  |  |  | Proposed
CE-DB-02 | Aurora writer failover — direct-connection | Data-Aurora | Infrastructure | Sync API | SAM (Core DB) | Same failover on a direct (non-proxy) cluster under load. | aws-jdbc-wrapper fast-failover redirects connections within pool timeout budget; documented behavior matches FMEA ledger. | FIS / failover-db-cluster | Core DB cluster | Error rate >5% / 3 min | Recovery time quantified; asymmetry vs CE-DB-01 documented as evidence for proxy adoption decision. | Same detection as DB-01. | Medium | Same caveats as DB-01. | 3 | 4 |  | 1 | CE-DB-01 |  |  | Proposed
CE-DB-03 | Connection storm on writer promotion | Data-Aurora | Compound | Sync API | SAM + heaviest callers | Writer failover while pools are near max and load is high — deliberate worst case. | HikariCP settings (max pool, connection timeout, validation) prevent thundering-herd reconnect storm from delaying promotion recovery. | FIS + load profile | Core DB + callers | DB CPU pegged >5 min | Reconnect ramp controlled; total brownout window within FMEA-assessed bound. | Pool saturation metrics visible pre-failure. | Low | Pool sizes & instance class differ in PERF — directional only; flag for PROD-parity retest. | 2 | 5 |  | 3 | CE-DB-02,CE-APP-05 |  |  | Proposed
CE-DB-04 | Reader node failure (reader/writer split) | Data-Aurora | Infrastructure | Sync API | Proxy-fronted ENRC services | Kill/reboot a reader instance under read-heavy load. | Reads redistribute to surviving readers/writer without error spike; reader endpoint DNS behavior within TTL budget. | FIS aws:rds:reboot-db-instances | One reader | Read errors sustained | Read continuity; latency bump bounded. | Reader loss alarmed distinctly from writer events. | High | — | 3 | 3 |  | 2 | CE-DB-01 |  |  | Proposed
CE-DB-05 | Global replication lag / stale-read tolerance | Data-Aurora | Infrastructure | All Aurora users | Global clusters | Induce/observe elevated cross-region replication lag (heavy write load; direct lag injection has no FIS action — method gap). | Services and DR runbooks tolerate documented lag; RPO assumptions (incl. DBE 'RPO PoF') hold under stress. | Custom (write-load driven) | Secondary region reads | Lag beyond RPO assumption | Measured lag vs documented RPO; consumers of secondary data behave. | Replication-lag alarm exists with correct threshold. | Low | Data volume in PERF understates PROD lag — treat as method validation. | 2 | 4 |  | 3 |  |  |  | Proposed
CE-DB-06 | Managed planned global failover | Data-Aurora | Infrastructure | All | Aurora Global (per cluster) | Execute managed planned failover us-east-1→us-east-2. | Failover completes within documented window; applications reconnect to new writer; replication reverses cleanly. | AWS managed operation | One global cluster | Failback risk identified | End-to-end timing evidence per cluster; app reconnect behavior per proxy/direct split. | Region-level DB alarms coherent during transition. | Medium | Cluster sizing deltas. | 2 | 4 |  | 3 | CE-DB-01,CE-DB-02 |  |  | Proposed
CE-DB-07 | Unplanned global failover (detach & promote) | Data-Aurora | Infrastructure | All | Aurora Global (per cluster) | Simulate region loss: detach secondary and promote (drill). | Promotion + app cutover meets RTO; data loss within RPO; procedure executable by on-call from runbook alone. | Drill (manual/scripted) | One global cluster + dependents | Any ambiguity in runbook | RTO/RPO evidence; stale-writer protection confirmed (see DB-08). | All failover alarms/dashboards correct in surviving region. | Low | PERF topology parity required; data volume affects timing. | 1 | 5 |  | 4 | CE-DB-06 |  |  | Proposed
CE-DB-08 | Stale writer endpoint after promotion | Data-Aurora | Application | All Aurora users | Sample per driver config | After promotion, verify no service continues writing to old-region endpoint (driver DNS caching, wrapper topology refresh). | aws-jdbc-wrapper topology awareness prevents split-brain writes; any cached-endpoint writes fail closed. | Post-drill verification + custom probe | Data integrity | Any write accepted by old writer | Zero writes to demoted writer; wrapper refresh timing quantified. | Cross-region write-attempt visibility exists (likely gap). | High | Driver behavior transfers. | 2 | 5 |  | 3 | CE-DB-06 |  |  | Proposed
CE-DB-09 | IAM auth token failure (aws-jdbc-wrapper) | Data-Aurora | Infrastructure | All (no static DB passwords) | One sync API | Deny IAM DB-auth token generation (perf-scoped IAM policy) for the service role. | Existing connections continue (token is connect-time only); NEW connections fail with clear error; pool contraction is alarmed before exhaustion. | Custom (IAM deny in PERF) | One service's new connections | Full pool exhaustion | Degradation curve understood; recovery instant on policy restore. | Auth-failure signature distinct in logs/alerts vs generic DB errors. | High | IAM mechanics identical across envs. | 2 | 4 |  | 2 |  |  |  | Proposed
CE-DB-10 | RDS Proxy endpoint unavailability | Data-Aurora | Infrastructure | Mixed (ENRC) | DCM, DBE, DTE | Block proxy endpoint (SG/NACL in PERF) — the proxy as its own failure point. | Services fail fast per timeout chain (no hang); recovery on restore without restart; proxy-as-SPOF risk quantified for the 3 ENRC services. | Custom (network deny) | ENRC DB access | Hang > timeout budget | Timeout chain honors documented order; no thread pile-up. | Proxy health distinct from cluster health in monitoring. | High | — | 2 | 4 |  | 2 | CE-EDGE-01 |  |  | Proposed
CE-CACHE-01 | ElastiCache primary failover | Cache | Infrastructure | Sync API / Event processor | Shared cluster users (ARM, AFM, DBE, DTE, DCM) | Fail over primary→replica on the shared Redis cluster. | Clients reconnect within seconds; brief error/latency blip absorbed by callers; no data-correctness impact. | FIS aws:elasticache / console failover | Shared cache | Errors sustained >2 min | Reconnect clean; SLI blip bounded. | Cache failover event alarmed. | High | — | 3 | 3 |  | 1 |  |  |  | Proposed
CE-CACHE-02 | Full cache cluster unavailable | Cache | Infrastructure | Sync API | ARM, AFM (cache-dependent APIs) | Block all access to Redis for the service under load. | Services degrade to Aurora-backed path (or defined degraded mode) — slower but correct; Aurora absorbs amplified read load. | Custom (SG deny) | Cache-dependent services | Aurora saturation | Correctness preserved; amplification factor measured (input to CE-CMP-05). | Cache-down + DB-amplification both visible. | Medium | Aurora headroom differs in PERF — amplification ratio transfers, absolute capacity doesn't. | 2 | 4 |  | 2 | CE-CACHE-01 |  |  | Proposed
CE-CACHE-03 | Cache auth token retrieval failure (VaultSM ASM) | Cache | Infrastructure | All cache users | One service | Deny ASM secret retrieval for Redis auth token; include a task recycle during the outage. | Running tasks unaffected (token held); RECYCLED tasks fail startup loudly, not silently degraded; no crash-loop masking. | Custom (ASM deny in PERF) | One service | Silent degraded serving | Startup-dependency risk quantified; crash-loop backoff sane. | Secret-retrieval failure alarmed distinctly. | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-CACHE-04 | Cold-cache stampede | Cache | Infrastructure | Sync API | ARM/AFM + Aurora | Flush cache under load; measure stampede onto Aurora. | Request coalescing / TTL jitter / warmer limits stampede; Aurora load stays under safe threshold. | Custom (FLUSH in PERF) | Cache + backing DB | Aurora saturation | Stampede controls proven or gap documented. | Amplification visible as leading indicator. | Medium | Absolute DB capacity differs. | 3 | 4 |  | 2 | CE-CACHE-02 |  |  | Proposed
CE-CACHE-05 | ElastiCache loss MID-RECON (EOD datastore) | Cache | Infrastructure | Recon/pipeline | DTR | Fail Redis while DTR is mid-reconciliation (EOD txn cache in use). | Recon detects datastore loss, fails safe (no partial/incorrect postings), and is restartable — re-pull from CBS EOD API rather than corrupt continuation. | FIS/console failover + custom timing | Recon run | ANY posting correction from bad state | No incorrect Posting-API corrections; rerun completes in window; Redis-as-datastore (not cache) risk documented. | Mid-run datastore loss pages recon on-call immediately. | High | Logic-level; file volumes smaller in PERF (timing caveat). | 2 | 5 |  | 2 | CE-CACHE-01,CE-PIPE-10 |  |  | Proposed
CE-CACHE-06 | Recon purge failure — memory accumulation | Cache | Detection | Recon/pipeline | DTR | Suppress the post-recon purge (step 10) across simulated cycles. | Memory-pressure trend is detected well before eviction threatens the next recon's EOD dataset. | Custom (skip purge in PERF) | Redis capacity trend | n/a (observation) | Days-to-failure runway quantified. | Trend alarm exists with adequate lead time (suspected gap). | High | Trend math transfers. | 2 | 4 |  | 2 |  |  |  | Proposed
CE-CACHE-07 | Post-regional-failover cold cache | Cache | Infrastructure | All cache users | Surviving-region Redis | Per-region static clusters ⇒ regional failover lands on a cold cache. Simulate by directing load at standby-region cache. | Surviving region absorbs cold-start read amplification during DR without breaching Aurora capacity. | Custom + load | Standby region | Aurora saturation | Cold-start curve measured; feeds DR capacity plan and CE-CMP-05. | Standby-region dashboards actually populated (validate). | Medium | Standby capacity parity TBD. | 3 | 4 |  | 3 | CE-CACHE-04 |  |  | Proposed
CE-KFK-01 | MBUS cluster unreachable | Messaging-Kafka | Infrastructure | Event processor + publishers | DBE, DTE, DSC, DAL, DSM, SAM, DCM, AFM | Blackhole network path to on-prem MBUS (C001/C002). | Consumers idle without crash-loop; producers buffer/queue per config without data loss or unbounded memory; full catch-up on restore with no gaps/dupes. | Custom (network blackhole PERF) | All Kafka traffic | Producer memory growth unbounded | Zero event loss post-restore; backlog drain time measured; producer overflow policy proven. | Broker-unreachable alarm + per-consumer lag visible. | High | Client behavior transfers; on-prem path is same class of fault as PROD DX loss. | 3 | 5 |  | 2 | CE-KFK-06 |  |  | Proposed
CE-KFK-02 | MBUS unreachable during EOD window | Messaging-Kafka | Compound | Recon + processors | DTR primarily | MBUS outage timed across CBS EOD Completion publication. | DTR's missing-trigger handling (see PIPE-06) engages; recon completes late-but-correct via defined recovery, inside business tolerance. | Custom timing | EOD processing | Recon SLA breach unmanaged | Recovery path exercised end-to-end; late-recon comms path (EDX/Ops) fires. | EOD-event-absence alarm with deadline semantics (suspected gap). | High | — | 2 | 5 |  | 3 | CE-KFK-01,CE-PIPE-06 |  |  | Proposed
CE-KFK-03 | Consumer rebalance storm | Messaging-Kafka | Infrastructure | Event processor | DBE or DTE | Repeatedly kill/restart consumer tasks to force serial rebalances. | Rebalance protocol (cooperative?) limits pause; no duplicate enrichment side-effects; lag recovers between storms. | FIS stop-task loop | One consumer group | Duplicate enriched events downstream | Processing-pause per rebalance quantified; assignment strategy validated. | Rebalance frequency alarmed as abnormal. | High | — | 3 | 3 |  | 2 | CE-COM-04 |  |  | Proposed
CE-KFK-04 | Poison message handling | Messaging-Kafka | Application | Event processor | DBE, DTE, DSC, DAL (each) | Publish malformed/contract-violating event to PERF topic. | Consumer parks/DLQs the message and CONTINUES — one bad event cannot halt the partition (classic head-of-line risk). | Custom producer (PERF topics) | One partition | Partition stalled >5 min | Skip/park behavior proven per consumer; replay procedure exists. | Poison/parked-message alarm fires with payload pointer. | High | Logic-level. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-KFK-05 | Duplicate delivery idempotency | Messaging-Kafka | Application | Event processor | DBE, DTE, DSC, DAL (each) | Re-publish already-processed events (at-least-once reality). | Every consumer is effectively idempotent: no duplicate enriched events to AU/ETU, no duplicate alerts to NOTIFY, no double cache writes. | Custom producer | Downstream consumers | Any duplicate side-effect | Idempotency proven per consumer per event type. | Duplicate-detection metrics exist (nice-to-have). | High | Logic-level. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-KFK-06 | Consumer lag accumulation & drain | Messaging-Kafka | Infrastructure | Event processor | DBE, DTE | Pause consumption (scale to 0) for a bounded window, then resume. | Backlog drains within recovery-time model; ordering preserved; downstream (AU/ETU) absorbs burst. | Scale-to-zero + resume | One consumer group | Retention risk approached | Drain rate measured ⇒ max tolerable outage derived (feeds KFK-01/02). | Lag alarm thresholds validated against real drain math. | Medium | Throughput differs in PERF; drain RATE transfers, absolute times don't. | 3 | 3 |  | 1 |  |  |  | Proposed
CE-KFK-07 | IDP OAUTHBEARER token failure (Kafka auth) | Messaging-Kafka | Infrastructure | All Kafka clients | One consumer + one producer | Block IDP token issuance for Kafka SASL auth; include re-auth boundary. | Existing sessions survive to re-auth boundary; failed re-auth backs off sanely (no auth-storm against IDP); clear failure signature. | Custom (IDP path block PERF) | Kafka connectivity | Auth retry storm | Session lifetime + backoff behavior documented; recovery clean. | Kafka-auth failure distinct from broker-unreachable in alerts. | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-KFK-08 | KMS key access denial — encrypted topics | Messaging-Kafka | Infrastructure | Publisher/consumer | DSM, DBE (subledger/balance event aliases) | Deny kms:Decrypt/Encrypt on topic keys for the service role. | Publish/consume fails closed with explicit KMS error; no silent drop; processing halts visibly and resumes on restore. | Custom (KMS key policy PERF) | Encrypted event flows | Silent event loss | Zero loss; halt-and-resume clean. | KMS-denial signature alarmed. | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-KFK-09 | PLACEHOLDER — Kafka SaaS migration scenario set | Messaging-Kafka | TBD | Event processor | TBD | Reserved: re-run KFK-01..08 against Kafka SaaS on AWS; add SaaS-specific faults (quota throttling, private-link path, provider AZ events). | TBD when platform selected. | TBD | TBD | TBD | TBD | TBD | TBD | Per user direction: placeholder only, do not plan yet. | 0 | 0 |  | 4 | CE-KFK-01 |  |  | Proposed
CE-PIPE-01 | Input file late/missing at cutoff | Pipeline-Recon | Application | Recon/pipeline | DTR + EDX path | Withhold RDF/ADF/CDF file for one bank past cutoff. | EventBridge SLA validator detects absence at cutoff and EDX email notification fires (narrative step 2a); recon for other banks proceeds unaffected. | Custom (withhold in PERF) | One bank's recon | Cross-bank impact | Per-bank isolation proven; notification content actionable. | SLA-validator alarm + email verified end-to-end. | High | Same mechanism as PROD. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-PIPE-02 | Corrupt / malformed input file | Pipeline-Recon | Application | Recon/pipeline | DTR (Lambda validate/parse) | Deliver structurally invalid and semantically invalid files. | Validation Lambda rejects cleanly; rejection reaches Ops/EDX; no partial ingestion poisons downstream SQS. | Custom file injection | One file's flow | Partial ingestion detected | Reject path + quarantine proven; reprocess-after-fix works. | Rejection alarmed with file identity. | High | — | 4 | 4 |  | 1 |  |  |  | Proposed
CE-PIPE-03 | Duplicate file delivery | Pipeline-Recon | Application | Recon/pipeline | DTR | Deliver the same file twice (and same-name-different-content variant). | Ingestion is idempotent by file identity; no duplicate transaction records enter reconciliation; conflict variant is flagged, not silently overwritten. | Custom file injection | One bank's recon | Duplicate records in recon set | Dedup keys proven; conflict handling explicit. | Duplicate-delivery event logged/alarmed. | High | — | 3 | 4 |  | 1 |  |  |  | Proposed
CE-PIPE-04 | Lambda throttling on large-file day | Pipeline-Recon | Infrastructure | Recon/pipeline | DTR chunking Lambda | Lower reserved concurrency in PERF + inject peak-size file set. | Throttled invocations retry via SQS without loss or duplication of chunks; end-to-end completes within window at degraded rate. | Custom (concurrency limit) | Chunking stage | Chunk loss or duplication | Exactly-once chunk effects; window math validated for peak day. | Throttle + queue-age alarms fire before SLA risk. | Medium | PERF file volumes smaller — use synthetic peak set. | 3 | 4 |  | 2 |  |  |  | Proposed
CE-PIPE-05 | SQS DLQ + redrive validation | Pipeline-Recon | Infrastructure | Recon/pipeline | DTR queues (+ DCM weekly-job queue) | Force message processing failures to exhaust receive count. | Messages land in DLQ (not lost, not infinitely retried); redrive procedure restores processing without duplication. | Custom (failure injection) | One queue | Message loss | maxReceiveCount/visibility tuned; redrive runbook proven. | DLQ depth alarm fires at first message. | High | — | 3 | 4 |  | 1 |  |  |  | Proposed
CE-PIPE-06 | Dual-trigger failure A: files present, CBS EOD event absent | Pipeline-Recon | Application | Recon/pipeline | DTR | Deliver files normally; suppress CBS EOD Completion event. | Recon does NOT start on partial trigger; absence is detected against a deadline; defined recovery (manual trigger / EOD API poll) exists and works. | Custom (event suppression PERF) | EOD recon | Recon starts on partial data | No premature recon; deadline detection + recovery path proven. | EOD-event-absence alarm with time semantics (suspected gap — narrative silent on this). | High | Design-gap probe — likely FINDING. | 3 | 5 |  | 1 |  |  |  | Proposed
CE-PIPE-07 | Dual-trigger failure B: EOD event present, files absent | Pipeline-Recon | Application | Recon/pipeline | DTR | Publish EOD event; withhold files. | Recon waits for file leg per step-4a note; combined absence handling matches PIPE-01 path; no empty-set recon marked successful. | Custom | EOD recon | Recon 'succeeds' on empty set | No false recon-success; Acct Closure event (step 9) NOT published for unreconciled day. | False-success guard alarmed. | High | — | 3 | 5 |  | 1 | CE-PIPE-01 |  |  | Proposed
CE-PIPE-08 | SLA-validator scheduler misfire / double-fire | Pipeline-Recon | Infrastructure | Recon/pipeline | DTR EventBridge | Disable rule for one window; separately duplicate-trigger it. | Missed validation window is itself detected (who watches the watcher); double-fire causes no duplicate notifications/side-effects. | Custom (rule manipulation PERF) | SLA validation | n/a | Validator idempotent; meta-monitoring exists or gap logged. | Scheduler failure visibility (suspected gap). | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-PIPE-09 | S3 recon-bucket unavailability / latency | Pipeline-Recon | Infrastructure | Recon/pipeline | DTR buckets | Deny bucket access mid-pipeline (PERF bucket policy). | Each stage fails visibly and resumes idempotently on restore; ack/anomaly file writes are not silently skipped. | Custom (bucket policy) | Recon storage | Silent skip of outputs | Stage-level retry/resume proven. | S3 access errors alarmed per stage. | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-PIPE-10 | Recon abort mid-run → restart idempotency | Pipeline-Recon | Application | Recon/pipeline | DTR | Kill recon service at defined checkpoints incl. AFTER some Posting-API corrections have been sent. | Restart produces exactly-once EFFECTS: no duplicate posting corrections, no re-sent Acct-Closure/Recon events, resumable from checkpoint. | FIS stop-task + checkpoint timing | Recon run + CBS postings | Any duplicate posting correction | Exactly-once effects proven at every checkpoint — the single highest-integrity-risk scenario in the catalog. | Partial-run state visible to Ops. | High | Logic-level; PERF CBS dedicated instance receives corrections — confirm reversibility. | 3 | 5 |  | 1 |  |  |  | Proposed
CE-PIPE-11 | Forced cutoff-mismatch → TransactionInquiry SOR fallback | Pipeline-Recon | Application | Recon/pipeline | DTR + Core Transaction Svc | Engineer EOD dataset gaps so lookups miss (LCDP/CBS cutoff skew per narrative 5a). | Fallback to Core TransactionInquiry engages per design; result parity with primary path; fallback latency doesn't blow the window. | Custom dataset manipulation | Recon matching | Mismatch mis-posted | Fallback correctness + performance measured. | Fallback-rate metric exists (leading indicator of cutoff drift). | High | — | 3 | 4 |  | 2 | CE-PIPE-10 |  |  | Proposed
CE-NET-01 | Inter-service latency / packet-loss injection | Network | Infrastructure | Sync API | Service pairs on critical path | FIS network latency/loss actions on Fargate tasks (requires fault-injection endpoints + pidMode:task — availability TBC, Open Items). | Latency propagates per timeout chain, not as hangs; loss triggers retries within budget without amplification. | FIS network actions (TBC) / fallback tc-sidecar | Selected pairs | SLI breach | Degradation graceful and bounded. | Latency SLIs per hop visible in Dynatrace. | High | — | 3 | 4 |  | 2 | CE-EDGE-01 |  |  | Proposed
CE-NET-02 | AZ impairment | Network | Infrastructure | All in-region | One AZ's subnets | Blackhole one AZ (FIS network blackhole / NACL). | Multi-AZ placement absorbs loss: ALB routes around, ECS reschedules, Aurora AZ redundancy holds; capacity floor per service ≥ requirement at N-1 AZ. | FIS / custom NACL | One AZ | Any single-AZ SPOF found | No service loses quorum/capacity below SLO; SPOFs enumerated if found. | AZ-level health visible; alarms not double-firing per task. | Medium | PERF AZ spread/capacity parity TBD. | 2 | 5 |  | 2 | CE-COM-02 |  |  | Proposed
CE-NET-03 | On-prem path loss (DX) — MBUS / GKP / on-prem API GW | Network | Infrastructure | Cross-cutting | MBUS clients, TE (GKP via Envoy), MCC (on-prem API GW) | Blackhole on-prem-bound routes. | Each on-prem dependency fails per its class: Kafka per KFK-01; TE's GKP calls fail fast with degraded UX; MCC serves from local store/S3 config without on-prem GW. | Custom (route blackhole PERF) | All on-prem traffic | TE hard-down | Blast radius of DX loss fully mapped — key DR planning input. | DX-path health alarmed as a NAMED failure domain (suspected gap). | High | Same failure class as PROD DX loss. | 2 | 5 |  | 2 | CE-KFK-01 |  |  | Proposed
CE-NET-04 | VPC endpoint (PrivateLink) failure | Network | Infrastructure | All | AWS service endpoints (TBC applicability) | Remove/deny a VPC endpoint used for AWS service access. | SDK calls fail visibly (no long hangs); dependency on each endpoint enumerated. | Custom (endpoint policy) | Per endpoint | Hangs beyond timeout | Endpoint dependency map produced. | Endpoint failures distinguishable in telemetry. | High | Confirm endpoint architecture first (Open Items). | 2 | 3 |  | 3 |  |  |  | Proposed
CE-EDGE-01 | Timeout chain ordering validation | Edge | Application | Sync API | One representative service per APG | Inject stepped latency BETWEEN each configured threshold: just above HikariCP, just below Feign/R4j, ALB idle, NLB idle (350s), API GW (29s). | Timeouts fire in the documented order from the timeout-alignment work; every layer's failure is attributable; no silent NLB drops or API-GW-first surprises. | App-level latency (Chaos Monkey for Spring Boot) + Toxiproxy | One call path | n/a (measurement) | Empirical firing order == documented order, per path. Deviations are FMEA findings. | Each layer's timeout distinguishable in traces. | High | Config-level; verify PERF configs == PROD (Open Items). | 4 | 4 |  | 1 |  |  |  | Proposed
CE-EDGE-02 | NLB idle-timeout behavior (350s silent drop) | Edge | Application | Sync API | Long-call paths; DSM external→internal NLB pair | Hold connections idle past 350s; observe RST-on-next-byte semantics through the double-NLB DSM path. | No legitimate call path approaches NLB idle limits; keepalive settings prevent surprise resets on reused connections. | Custom client | Selected paths | n/a | Keepalive < NLB idle proven per hop. | Connection-reset anomalies visible. | High | — | 2 | 3 |  | 2 | CE-EDGE-01 |  |  | Proposed
CE-EDGE-03 | API Gateway throttle breach | Edge | Infrastructure | Sync API | One API per APG | Drive load past configured rate/burst limits. | 429s returned cleanly; callers back off (no retry hammering); throttle limits match capacity math. | Load generator | One API | Retry amplification | Backoff-on-429 proven caller-side. | Throttle events alarmed with caller attribution. | High | Limits config parity TBC. | 3 | 3 |  | 2 |  |  |  | Proposed
CE-EDGE-04 | ALB drain during deploy under load | Edge | Infrastructure | Sync API | One service | Deploy under load; measure deregistration-delay vs in-flight request duration. | Zero in-flight kills: drain timeout ≥ p99 request duration; connection reuse doesn't route to draining targets. | Deploy + load | One service | 5xx during drain | Drain settings validated against real p99. | Deploy-window error attribution clean. | High | — | 3 | 3 |  | 2 | CE-COM-03 |  |  | Proposed
CE-EDGE-05 | DPS Proxy path degradation (3-active edges) | Edge | Infrastructure | Edge/BFF | TE, CHE, SSE | Degrade one region's DPS-Proxy-fronted path (latency/errors upstream of R53). | 3-active routing shifts traffic away from impaired region; stateless services show no session breakage; user-visible impact bounded. | Custom (upstream injection) / coordination | One region's edge | User-visible errors sustained | Traffic-shift behavior measured incl. shift-back. | Regional edge health per region visible. | Low | us-west-2 presence + DPS Proxy parity in PERF TBC (Open Items). | 2 | 4 |  | 3 |  |  |  | Proposed
CE-EDGE-06 | DLAT direct path (no API GW) exposure check | Edge | Application | Admin tool | DLAT | Exercise DLAT's R53→NLB→ALB path under fault (latency, auth anomalies). | Protections absent from skipping API GW (throttle, auth at edge) are compensated elsewhere — or documented as accepted risk. | Custom | DLAT | n/a | Control gap analysis complete (feeds DLAT documentation gap). | DLAT traffic observable at all (suspected gap). | High | — | 2 | 3 |  | 3 |  |  |  | Proposed
CE-EXT-01 | CBS Posting 5xx burst | External Dep | Application | Sync API / Recon | AFM, DCM, DTR corrections | Inject 5xx from CBS Posting via proxy layer in front of dedicated PERF CBS instance. | R4j breaker on the Posting client trips on failure-rate; callers queue/park work per design; no lost postings — retried or parked, never dropped. | Toxiproxy/injection proxy (PERF CBS is live — cannot be failed itself) | Posting-dependent flows | Posting silently dropped | Breaker + park/retry semantics proven; recovery drains parked work. | CBS-Posting health as seen FROM Core alarmed (not just CBS's own monitoring). | High | Dedicated PERF CBS: inject in front, never break the instance. | 3 | 5 |  | 1 |  |  |  | Proposed
CE-EXT-02 | CBS slow-but-alive (gray failure) | External Dep | Application | Sync API | AFM, DSM, DCM (CBS callers) | Inject 5–15s latency (no errors) on CBS responses. | SLOW-CALL-RATE breaker path trips (distinct code path from failure-rate); threads don't pool-exhaust waiting; timeout chain caps caller exposure. | Toxiproxy latency | CBS callers | Thread pool exhaustion | Slow-call breaker config proven per service — the highest-value app-level test in the catalog. | Latency-based alerting fires BEFORE error-based. | High | — | 4 | 5 |  | 1 | CE-EDGE-01 |  |  | Proposed
CE-EXT-03 | CBS event stream stall | External Dep | Application | Event processor | DBE, DTE | Suppress CBS Balance/Transaction events (consumers healthy, topic silent). | Silence is DETECTED as anomaly (expected-throughput heartbeat), not just absence of errors — classic silent-failure trap. | Custom (suppress at source/proxy) | Enrichment freshness | n/a (detection) | Staleness of enriched data downstream (AU/ETU) bounded + alarmed. | Throughput-floor / heartbeat alarm exists (suspected gap). | High | — | 3 | 4 |  | 1 |  |  |  | Proposed
CE-EXT-04 | LCDP degradation | External Dep | Application | Per dependency map | LCDP callers | Inject errors/latency on LCDP calls. | Callers degrade per design (fallback/cached/deferred) without journey hard-failure where FMEA says soft-fail. | Toxiproxy | LCDP callers | Hard failure where soft expected | Documented degradation mode matches reality. | LCDP-as-seen-from-Core health visible. | High | — | 3 | 4 |  | 2 |  |  |  | Proposed
CE-EXT-05 | AU / ETU unavailable (enriched-event downstream) | External Dep | Application | Event processor | DBE→AU, DTE→ETU paths | Block delivery of enriched events to AU/ETU (Kafka-side or consumer-side per topology). | Enriched events are durable in MBUS regardless of downstream health (pub/sub decoupling holds); no producer-side blocking. | Custom | Enrichment egress | Producer blocked by consumer health | Decoupling proven; downstream catch-up clean. | Downstream-lag-on-our-topics visibility (whose alarm? — governance note). | High | — | 2 | 3 |  | 2 |  |  |  | Proposed
CE-EXT-06 | CSU failure — alert enrichment | External Dep | Application | Event processor | DAL | Fail CSU (parent/child fetch) during alert processing. | DAL degrades per design: alert sent without enrichment OR parked for cron recovery (its documented failure-recovery scheduler) — never silently dropped. | Toxiproxy | Alert pipeline | Alerts dropped | Degrade-vs-park decision proven; cron recovery drains parked alerts. | Unenriched/parked alert rate alarmed. | High | — | 3 | 3 |  | 2 |  |  |  | Proposed
CE-EXT-07 | ChannelContext failure — TE | External Dep | Application | Edge/BFF | TE | Fail ChannelContext calls from TE. | TE renders degraded-but-usable experience (partial data) rather than error page — BFF partial-failure rendering proven. | Toxiproxy | TE UX | Full page failure | Partial-render behavior per widget documented. | Client-visible degradation measured (RUM/synthetic). | High | — | 3 | 3 |  | 2 |  |  |  | Proposed
CE-EXT-08 | Split.io flag evaluation unavailable | External Dep | Application | All flag users | Per-service inventory | Block Split.io from services. | Each service's fail-open/fail-closed posture per flag is KNOWN and safe; cached/default treatments engage; no feature flapping. | Custom (egress block) | Flag-gated behavior | Unsafe default exposed | Flag-posture inventory produced per service — output is the deliverable. | Flag-evaluation failure visible. | High | — | 2 | 4 |  | 2 |  |  |  | Proposed
CE-EXT-09 | AuthAnywhere token issuance failure — TE ingress | External Dep | Application | Edge/BFF | TE (API GW token validate) | Degrade AuthAnywhere validation path at TE's edge. | Existing sessions (cached validations) continue per TTL; new sessions fail with clean auth error; no retry storm against IDP. | Custom / coordination | TE ingress auth | Auth retry storm | Session-cache behavior + backoff proven. | Auth-path failure distinct in alerting. | Medium | IDP is shared platform — coordination required; scope to PERF path. | 2 | 5 |  | 2 |  |  |  | Proposed
CE-CFG-01 | Parameter Store reload failure | Config/Secrets | Application | Event processor | DBE (parameterstore reload strategy) | Block Parameter Store access AFTER startup; then push a config change during the block. | Service continues on last-known-good config (no crash); missed reload is DETECTED; reload resumes on restore without restart. | Custom (deny in PERF) | DBE config | Crash on reload failure | Stale-config runway understood; reload health visible. | Reload-failure alarm exists (suspected gap). | High | — | 2 | 3 |  | 2 |  |  |  | Proposed
CE-CFG-02 | Secrets retrieval outage at task startup | Config/Secrets | Infrastructure | All | One service per secret pattern | ASM/Secrets Manager outage window + force task recycles during it. | Running tasks unaffected; replacement tasks fail startup FAST and LOUD; crash-loop backoff doesn't mask the root cause; capacity floor alarmed. | Custom (deny) + stop-task | Recycled tasks | Capacity below floor | Startup-dependency blast radius = f(recycle rate during outage) — quantified. | Startup-failure cause attributable in alerts. | High | — | 2 | 4 |  | 2 | CE-CACHE-03 |  |  | Proposed
CE-REG-01 | R53 failover + client re-resolution vs TTL | Region/DR | Infrastructure | Sync API | Active/Passive services | Execute DNS failover; measure ACTUAL client re-resolution against the TTL-floor finding from prior DR work. | Traffic shifts within TTL-derived budget; long-lived connections re-resolve (or are forcibly recycled) per design; no stragglers pinned to failed region. | Drill + client-side measurement | One service's traffic | Stragglers writing to old region | Empirical re-resolution curve vs TTL floor — closes the prior finding. | Traffic-shift completeness measurable per region. | Low | PERF DNS config parity + client population differ — treat as method validation, retest at prod-parity. | 3 | 4 |  | 4 |  |  |  | Proposed
CE-REG-02 | dr-orchestrator orchestrated failover — full drill | Region/DR | Compound | Orchestrator | dr-orchestrator + one APG scope | Trigger the CloudWatch-alarm-driven orchestrated failover end-to-end (clean-room conditions first). | Orchestrator sequences DNS/DB/service failover correctly; per-step evidence matches design; RTO within target for the scoped APG. | Drill (alarm-triggered) | Scoped APG cross-region | Any step requiring undocumented manual fix | Step-by-step timing evidence; the orchestrator is the system under test. | Orchestrator's own telemetry sufficient to follow progress live. | Medium | dr-orchestrator PERF parity TBC (Open Items). | 2 | 5 |  | 4 | CE-DB-06,CE-REG-01 |  |  | Proposed
CE-REG-03 | Orchestrator impaired DURING failover | Region/DR | Compound | Orchestrator | dr-orchestrator | Fail dr-orchestrator mid-sequence (kill at defined steps). | Partial-failover state is safe (no split-brain), diagnosable, and manually completable from runbook — the orchestrator is not a new SPOF. | Drill + injection | Failover state machine | Split-brain risk | Manual completion path proven per interruption point. | Partial-state visibility explicit. | Medium | Highest-risk drill — schedule with full stakeholder cover. | 1 | 5 |  | 4 | CE-REG-02 |  |  | Proposed
CE-REG-04 | Active/Active brownout (latency-routed) | Region/DR | Infrastructure | Sync API | ALS, ARM | Degrade (not kill) one region — elevated latency/errors below failover thresholds. | Latency-based routing shifts weight gracefully; no oscillation; brownout (gray) handled as well as blackout. | Custom regional degradation | One region's share | Route flapping | Shift + shift-back smooth; hysteresis adequate. | Per-region SLI split visible for A/A services. | Medium | Routing config parity TBC. | 3 | 4 |  | 4 | CE-REG-01 |  |  | Proposed
CE-REG-05 | 3-Active regional loss — experience services | Region/DR | Infrastructure | Edge/BFF | TE, CHE, SSE | Remove one of three regions for stateless experience tier. | Remaining two regions absorb at N+1 capacity; stateless claim proven (no hidden affinity); UX impact ~zero. | Drill | One region of three | UX errors | Hidden-state findings (if any) enumerated. | Tri-region dashboards coherent. | Low | us-west-2 presence in PERF TBC; SSE blocked on documentation. | 2 | 3 |  | 4 | CE-EDGE-05 |  |  | Proposed
CE-REG-06 | MCC Pilot Light activation | Region/DR | Compound | Sync API + pipeline | MCC | Activate MCC's pilot-light DR: stand up capacity, restore data path, cut over. | Activation runbook meets MCC's RTO; ETU scheduled pull resumes in DR region exactly once; S3 config current. | Drill | MCC | RTO blown badly | Pilot-light RTO evidence — different posture, different proof. | DR-region MCC monitored from cold start. | Low | Pilot-light infra existence in PERF TBC (Open Items). | 1 | 4 |  | 4 |  |  |  | Proposed
CE-REG-07 | Regional failover MID-RECON window | Region/DR | Compound | Recon/pipeline | DTR | Execute regional failover while DTR is mid-run (cross-region S3 + bidirectional Aurora + regional Redis EOD cache). | Recon state survives or safely restarts in DR region: S3 CRR current, Aurora consistent, Redis EOD cache REBUILT from CBS EOD API (it does not replicate). | Drill + timing | EOD recon + region | Posting corrections from inconsistent state | Recon-in-DR completes correct-and-late at worst; Redis rebuild path proven. | Recon-state dashboards exist in BOTH regions. | Medium | Combines CACHE-05 + REG mechanics. | 1 | 5 |  | 4 | CE-CACHE-05,CE-REG-02 |  |  | Proposed
CE-REG-08 | Cross-posture cascade — 3-active edge → failing-over A/P API | Region/DR | Compound | Edge + Sync API | TE/CHE → SAM/AFM path | Regional event where edge tier stays tri-region but its downstream sync APIs are mid-A/P-failover. | Edge retries/timeouts against the failing-over region don't amplify; edge routes to surviving-region API endpoints per discovery design; UX degraded not down. | Drill scenario within REG-02 scope | Edge→API paths | Retry amplification | Posture-mismatch window quantified — unique to your mixed-posture estate. | Cross-region call-path visibility in traces. | Medium | — | 2 | 4 |  | 4 | CE-REG-02,CE-APP-03 |  |  | Proposed
CE-OBS-01 | Detection baseline — Dynatrace coverage & latency | Observability | Detection | All | Wave-1 fault set | For every Wave-1 injection, record: detected? alerted? paged? time-to-detect? correct component blamed? | Dynatrace (SaaS) detects ≥ agreed % of injected faults within target latency with correct root-cause attribution — validating the 'not configured properly' concern with evidence. | Piggyback on Wave-1 runs | n/a | n/a | Coverage/latency scorecard per fault class — THE Wave-1 deliverable for leadership. | This scenario IS the detection criterion. | Medium | Dynatrace config should be env-agnostic — confirm same monitoring config deployed to PERF. | 5 | 4 |  | 1 |  |  |  | Proposed
CE-OBS-02 | CloudWatch alarm validation — dr-orchestrator triggers | Observability | Detection | Orchestrator | Failover-trigger alarms (owned outside app repos) | Inject the exact conditions each failover-trigger alarm watches; verify firing thresholds/timing. | Every alarm that can trigger orchestrated failover fires when it should and NOT on Wave-1 single-fault noise (false-trigger risk). | Coordination with alarm owners + injection | Alarm set | Accidental failover trigger — HARD ABORT | Trigger-alarm truth table produced; false-positive resistance proven. | n/a (is detection) | Medium | Alarm ownership is external — governance path in Open Items. | 3 | 5 |  | 1 |  |  |  | Proposed
CE-OBS-03 | Silent-failure probes | Observability | Detection | Event processor / pipeline | DSC warmer stop; DTR purge skip; DBE reload block | Stop things that fail SILENTLY by design shape (no errors, just absence of good behavior). | Absence-of-work is alarmed: warmer heartbeat, purge success metric, reload freshness — or gaps are logged as findings. | Custom per probe | None (observation) | n/a | Silent-failure gap list — expected to be the richest finding source. | n/a (is detection) | High | — | 4 | 4 |  | 1 |  |  |  | Proposed
CE-OBS-04 | Detection-to-diagnosis drill (on-call) | Observability | Detection | All | On-call rotation | Unannounced (within game-day window) fault; measure alert→ack→correct-diagnosis→correct-runbook time. | Human + tooling loop reaches correct diagnosis within target; runbooks match reality post-Wave-1/2 findings. | Game day | One team's on-call | Distress — abort and debrief | MTTD/MTTI evidence; runbook fixes queued. | n/a (is detection) | High | — | 3 | 4 |  | 3 | CE-OBS-01 |  |  | Proposed
CE-APP-01 | Breaker trip — failure-rate path + half-open recovery | App Resilience | Application | Sync API | Each R4j-protected client (start: CBS clients) | Inject 5xx bursts at/above failure-rate threshold; then heal and observe half-open probing. | Breaker opens at configured rate; fallback engages; half-open probes recover WITHOUT flapping under partial healing. | Toxiproxy / app-level | One client | Flapping open/closed | Config values empirically confirmed per client. | Breaker state transitions visible + alarmed on open. | High | Config-level. | 4 | 4 |  | 1 |  |  |  | Proposed
CE-APP-02 | Breaker trip — SLOW-CALL-rate path | App Resilience | Application | Sync API | Same clients as APP-01 | Inject latency (no errors) at/above slow-call threshold. | Slow-call breaker path trips — DISTINCT config and code path from failure-rate; services with only failure-rate configured are found now, not in an incident. | Toxiproxy latency | One client | Thread exhaustion | Slow-call config presence/values confirmed per client. | Slow-call breaker events distinguishable from error-trips. | High | — | 4 | 5 |  | 1 | CE-APP-01 |  |  | Proposed
CE-APP-03 | Retry amplification under partial failure | App Resilience | Application | Sync API chain | Multi-hop path (edge→API→CBS) | 30–50% downstream failure rate; observe retry multiplication up the chain. | Retry budgets + jitter + breaker interplay cap amplification ≤ agreed factor; a 30% degradation cannot become 3x load (the classic self-DDoS). | Toxiproxy partial failure | One call chain | Load amplification >2x | Amplification factor per chain measured. | Retry-rate metrics visible per client. | High | — | 4 | 5 |  | 1 | CE-APP-01 |  |  | Proposed
CE-APP-04 | Bulkhead / thread-pool exhaustion | App Resilience | Application | Sync API | One service, multi-dependency | Saturate one dependency's calls; verify OTHER endpoints of the same service stay healthy. | Bulkhead isolation holds: one slow dependency cannot consume the shared thread pool and take down unrelated endpoints. | Toxiproxy + load | One service internals | Unrelated endpoints failing | Isolation proven or bulkhead gap found per service. | Per-pool saturation metrics exposed. | High | — | 3 | 4 |  | 2 | CE-APP-02 |  |  | Proposed
CE-APP-05 | HikariCP pool exhaustion under downstream latency | App Resilience | Application | Sync API | One Aurora-heavy service | Slow DB responses (Toxiproxy on DB path in PERF) until pool saturates. | connectionTimeout fails-fast waiting threads per timeout chain; pool recovers without restart; sizing math validated against thread model. | Toxiproxy on DB path | One service | Hang > chain budget | Pool config empirically validated (input to CE-DB-03). | Pool wait/saturation alarmed before request failures. | High | — | 3 | 4 |  | 1 | CE-EDGE-01 |  |  | Proposed
CE-APP-06 | Heap pressure / GC brownout | App Resilience | Application | Sync API | One JVM service | Gradual memory assault to force sustained GC pressure (not instant OOM — the gray zone). | GC-driven latency degradation is detected and the task is recycled by health checks BEFORE prolonged brownout serving. | Chaos Monkey for Spring Boot memory assault | One task | Brownout > 5 min | Health-check sensitivity to gray degradation proven. | GC/latency correlation alerting exists. | High | — | 3 | 3 |  | 2 | CE-COM-07 |  |  | Proposed
CE-CMP-01 | Writer failover + saturated pools | Compound | Compound | Sync API | SAM + callers | CE-DB-02 under CE-APP-05 preconditions — failover at worst moment. | Combined recovery ≤ FMEA-assessed bound; no deadlock between reconnect storm and pool timeout behavior. | FIS + Toxiproxy + load | Core DB + callers | Brownout > bound | Worst-case failover envelope quantified. | Combined-fault telemetry still attributable. | Low | Capacity-sensitive — directional in PERF. | 2 | 5 |  | 3 | CE-DB-02,CE-APP-05 |  |  | Proposed
CE-CMP-02 | AZ loss during rolling deployment | Compound | Compound | Sync API | One service | CE-NET-02 injected mid-deploy. | min-healthy + AZ rebalance interact safely; deploy halts/rolls back rather than compounding capacity loss. | FIS + pipeline | One service | Capacity < floor | Interaction proven safe. | Operator can distinguish deploy vs AZ signal live. | Medium | — | 2 | 4 |  | 3 | CE-NET-02,CE-COM-03 |  |  | Proposed
CE-CMP-03 | Dependency latency + retry storm cascade | Compound | Compound | Multi-service | Edge→AFM→CBS chain | CBS gray failure (EXT-02) + realistic edge traffic — watch the cascade attempt. | Breakers + retry budgets contain the cascade at first hop; edge sheds gracefully; no cross-APG contagion. | Toxiproxy + load | One journey chain | Contagion beyond chain | Containment proven end-to-end — the marquee compound scenario. | Cascade visible as coherent story in Dynatrace. | Medium | — | 3 | 5 |  | 3 | CE-APP-02,CE-APP-03 |  |  | Proposed
CE-CMP-04 | IDP platform outage — Kafka auth + API OAuth together | Compound | Compound | Cross-cutting | All IDP consumers | Simulate ADFS-IDP unavailable: Kafka OAUTHBEARER (KFK-07) AND TE ingress (EXT-09) simultaneously — IDP is a shared single point. | Session/token caching keeps platform functional for cache lifetime; degradation is gradual and alarmed, not cliff-edge; recovery has no auth stampede. | Custom coordinated block | Platform-wide auth | Cliff-edge failure | IDP blast radius fully mapped — leadership-grade finding either way. | Platform-auth degradation has a single coherent alert story. | Medium | Coordinate scope with platform team. | 2 | 5 |  | 3 | CE-KFK-07,CE-EXT-09 |  |  | Proposed
CE-CMP-05 | Regional failover + cold cache + Aurora capacity | Compound | Compound | All | Surviving region | CE-CACHE-07 amplification during actual regional cutover load shift. | Surviving-region Aurora absorbs (shifted load × cold-cache amplification factor from CACHE-02/04) with headroom. | Drill component within REG scope | Surviving region | Aurora saturation | DR capacity model validated with measured amplification, not assumptions. | Capacity-headroom alarms lead errors. | Low | Capacity-sensitive. | 2 | 5 |  | 4 | CE-CACHE-07,CE-REG-02 |  |  | Proposed
CE-CMP-06 | GAME DAY — region impairment during peak posting window | Compound | Compound | All + Orchestrator | Full journey scope incl. dr-orchestrator, DTR | Full narrative: region degrades during peak activity approaching EOD; alarm-triggered orchestrated failover; recon window at risk; on-call drives. | The PROGRAM's thesis: journeys survive a realistic worst-day with degraded-not-down UX, correct data, recon completing late-but-right, and humans in control throughout. | Game day (all prior tooling) | Full PERF estate | Safety/abort per runbook | End-to-end evidence pack for leadership — the capstone. | Full-stack observability tells one coherent story. | Medium | Capstone — requires Waves 1–3 confirmed. | 1 | 5 |  | 4 | CE-REG-02,CE-REG-07,CE-CMP-03,CE-OBS-04 |  |  | Proposed

## Priority Model
Dimension | Score | Tier / Label | Definition
Likelihood | 5 | Almost Certain | Expected routinely in normal operations (task recycles, single-node events, transient dependency errors).
Likelihood | 4 | Likely | Expected multiple times per year (consumer rebalances, duplicate event delivery, malformed inputs, gray dependency latency).
Likelihood | 3 | Possible | Plausible annually (writer failover, cache failover, AZ impairment, message-broker outage, throttling events).
Likelihood | 2 | Unlikely | Rare but credible (regional service degradation, IAM/KMS policy faults, identity-provider outage, proxy endpoint loss).
Likelihood | 1 | Rare | Exceptional (full region loss, orchestrator failure mid-failover).
Severity | 5 |  | Data integrity / financial correctness at risk (duplicate writes, incorrect reconciliation, split-brain writes) OR platform-wide outage OR a missed critical processing obligation.
Severity | 4 |  | Journey outage or major degradation for one or more critical journeys; unrecoverable-without-human events.
Severity | 3 |  | Single-service degradation with journey-level slowdown; self-healing expected.
Severity | 2 |  | Localized, transient, absorbed by redundancy; customer-invisible if systems behave.
Severity | 1 |  | Negligible customer/system impact; hygiene validation.
Priority | L × S |  | Computed in the catalog (column R) as Likelihood × Severity. Risk Rating (column Y): 16–25 = Critical; 9–15 = High; 4–8 = Medium; 1–3 = Opportunistic.
Wave | 1 | Foundation | Detection baseline + isolated singles with contained blast radius + integrity-critical logic tests (idempotency, dual-trigger, breaker paths, timeout chain).
Wave | 2 | Breadth | Remaining singles across all fault domains; infra faults needing custom tooling; external-dependency injection.
Wave | 3 | Depth | Compounds + coordination-heavy scenarios; on-call drills. Entry: prerequisite singles Confirmed.
Wave | 4 | Capstone | Region/DR drills, orchestrated-failover under test, pilot-light/DR-posture activation, capstone game day. Entry: Waves 1–3 evidence pack + stakeholder sign-off.
Rule | — |  | A scenario's Wave may never precede any of its Prereq IDs' waves. Likelihood/Severity are proposals — recalibrate against your organization's incident history / FMEA ledger during the FMEA-Ref mapping pass, and again once the code/infra scan (see App & Infra Scan Instructions tabs) produces real evidence.
Likelihood Tier Distribution (live from Scenario Catalog)
Tier | Count
Almost Certain
Likely
Possible
Unlikely
Rare
Total
Risk Rating Distribution (live from Scenario Catalog)
Rating | Count
Critical
High
Medium
Opportunistic
Total

## Wave Plan
Wave | Theme | Entry Criteria | Exit Criteria | # Scenarios (live) | Sum Priority (live)
1 | Detection baseline + contained singles + integrity logic (idempotency, dual-trigger, breaker both paths, timeout chain, DSM state, recon restart) | PERF load harness ready; FIS onboarded; Dynatrace/CloudWatch access for evidence capture; game-day runbook + abort authority named. | ≥80% of Wave-1 scenarios Executed; detection scorecard (CE-OBS-01) published; findings triaged into FMEA ledger; steady-state gaps listed.
2 | Full single-fault breadth: data/cache/kafka/pipeline/network/edge/external/config | Wave-1 exit met; custom tooling built (Toxiproxy layer, IAM/KMS/ASM deny scripts, file injectors, event suppressors); FIS Fargate network actions confirmed or tc-fallback ready. | All fault domains have ≥1 Confirmed scenario; per-service resilience-config truth table (breaker/retry/pool) published.
3 | Compounds, cascades, on-call drills | Prereq singles Confirmed; blast-radius model per compound approved; alarm owners engaged (CE-OBS-02 done). | Compound envelope evidence (failover-under-saturation, cascade containment, IDP blast radius); MTTD/MTTI baseline from drills.
4 | Region/DR: R53, orchestrated failover, orchestrator-under-test, pilot light, mid-recon failover, capstone game day | Waves 1–3 evidence pack; leadership sign-off; dr-orchestrator PERF parity confirmed; rollback/abort rehearsed. | RTO/RPO evidence per DR posture (A/A, A/P, 3-Active, Pilot Light); capstone game-day report — the program's leadership deliverable.
TOTAL

## Coverage Matrix
Scenario counts by Fault Domain × Wave (live from catalog)
Fault Domain | Wave 1 | Wave 2 | Wave 3 | Wave 4 | Total
Compute
Resource
Data-Aurora
Cache
Messaging-Kafka
Pipeline-Recon
Network
Edge
External Dep
Config/Secrets
Region/DR
Observability
App Resilience
Compound
TOTAL
Scenario counts by Injection Plane
Injection Plane | Count
Infrastructure
Application
Compound
Detection
TBD

## Open Items
# | Item | Why it matters / what it gates | Owner | Status
1 | RDS Proxy split confirmation | Diagram silence ≠ proof of direct connection (per your table's own caveat). CE-DB-01/02 asymmetry design assumes proxy = DCM/DBE/DTE only. Enrique checking. | Enrique | Open
2 | FMEA Ref mapping | Map all 90 scenarios to existing FMEA scenario IDs (ASSESSED items first). Recalibrate L/S scores against ledger values during the pass. | Chaos team | Open
3 | Journey mapping | Populate Journeys column against the official 16-journey list; journey criticality then feeds wave-1 sub-ordering. | Chaos team | Open
4 | Dynatrace PERF config parity | 'Team hasn't configured things properly' — CE-OBS-01 validates coverage, but first confirm the SAME monitoring config is deployed to PERF, else the scorecard measures the wrong thing. | Chaos + Obs team | Open
5 | PERF↔PROD delta register | Formal list: task counts/scaling, Aurora instance classes, data volumes, us-west-2 presence for 3-Active tier, pilot-light infra for MCC, R53/DNS config, dr-orchestrator parity, timeout config parity. Every 'Medium/Low PERF validity' flag resolves against this register. | Enrique + Chaos team | Open
6 | FIS Fargate network actions availability | Latency/loss/blackhole on Fargate needs fault-injection endpoints + pidMode:task and no blocking SCPs. If unavailable → build tc-sidecar fallback (gates CE-NET-01/02). | Chaos team | Open
7 | External-dependency injection layer | Decide and build the Toxiproxy (or equivalent) layer in front of dedicated PERF CBS + LCDP/CSU/ChannelContext paths. PERF CBS is live — inject in front, never break it. Gates all CE-EXT. | Chaos team | Open
8 | CloudWatch alarm ownership | Failover-trigger alarms owned outside app repos — CE-OBS-02 requires their owners at the table; false-trigger risk makes this a governance item, not a courtesy. | Enrique | Open
9 | Spend-Track documentation | No artifact exists. All SSE scenarios blocked until minimum documentation lands. Finding in itself. | Service team | Blocked
10 | DLAT dependency documentation | Infra-only diagram; CE-EDGE-06 doubles as the discovery exercise. | Service team | Open
11 | Kafka SaaS placeholder | CE-KFK-09 reserved. Re-plan KFK family when platform is selected. Per direction: no planning now. | — | Parked
12 | VPC endpoint architecture | Confirm PrivateLink/endpoint usage before CE-NET-04 is scoped. | Enrique | Open
13 | Recon reversibility in PERF CBS | CE-PIPE-10 sends real Posting corrections to the dedicated PERF CBS — confirm test postings are reversible/isolated before executing. | Chaos team | Open
14 | Steady-state SLI gaps | Any Wave-1 scenario without a trusted steady-state signal gets logged here and becomes an observability work item before execution. | Chaos team | Standing

## App Scan Instructions
Application Code Scan — Method & Standard
Durable reference for scanning ANY application repo for chaos-relevant, resilience-relevant facts. Written to be re-run unchanged on new services built after this catalog. Applies to Maven multi-module repos (root/parent pom.xml + one pom.xml per module) by default — adapt the build-file parsing step for other build tools.
Non-negotiable rules (apply to every category below)
• Every extracted fact carries evidence: {file path, line number, verbatim snippet}. No fact without evidence.
• Never assume a framework default. If a value isn't explicitly configured, record NOT_CONFIGURED — <library>@<version> default in effect and name the version; do not state what that default is unless verified against that exact version's documentation, and mark it a human-verify item if stated.
• A value only resolvable through Maven property inheritance or a profile-activated override that cannot be statically traced is AMBIGUOUS, with both candidate values and their sources recorded — never silently pick one.
• Config sourced from Secrets Manager / Parameter Store / VaultSM-ASM-style vaults (i.e., the key exists in code but the value is externally resolved) is EXTERNAL_CONFIG — not resolvable from repo. Do not attempt to guess the resolved value.
• A category with genuinely nothing found is NOT_FOUND, with the search patterns used listed — a clean sheet is a finding, not a skipped row.
• Status vocabulary is exactly: CONFIRMED ¦ NOT_FOUND ¦ NOT_CONFIGURED ¦ AMBIGUOUS ¦ EXTERNAL_CONFIG ¦ NOT_APPLICABLE. Do not invent new statuses.
Scan categories
Category | What to Extract | Where to Look (signals / patterns) | Evidence to Capture | Feeds Fault Domain(s) / Scenario Family
Dependency & Version Census | Build tool, resolved versions of: Spring Boot, Resilience4j, Feign/OpenFeign, HikariCP, Kafka client, AWS SDK (v1/v2), RDS/Aurora JDBC driver (aws-jdbc-wrapper or plain), Redis client. Version pins what a 'default' even means. | Root/parent pom.xml <properties>/<dependencyManagement>; each module pom.xml; run `mvn help:effective-pom` if Maven+JDK available on the scanning host for guaranteed resolution, else static multi-file parsing (mark inherited-but-unresolved properties AMBIGUOUS). | artifactId, resolved version, resolution method (effective-pom vs static), source file(s). | Feeds every other category below — versions gate what 'not configured' means.
Resilience Config (circuit breakers, retry, bulkhead) | Every @CircuitBreaker/@Retry/@Bulkhead/@RateLimiter annotation (or programmatic Resilience4j registry config): instance name, failureRateThreshold, slowCallRateThreshold + slowCallDurationThreshold, waitDurationInOpenState, permittedNumberOfCallsInHalfOpenState, whether a fallbackMethod actually exists and its signature matches, retry maxAttempts/backoff/jitter, bulkhead maxConcurrentCalls. | @CircuitBreaker/@Retry/@Bulkhead/@RateLimiter annotations; resilience4j.* keys in application*.yml; any programmatic CircuitBreakerConfig/RetryConfig builders. | Per protected call: client/method name, every configured threshold with file:line, presence/absence of slow-call config specifically (most common gap), fallback method existence. | App Resilience family (breaker/retry/bulkhead scenarios); directly assigns targets for slow-call-path experiments.
Timeout Chain (app-side) | Every timeout value in the request path: HikariCP connectionTimeout/maxLifetime/idleTimeout, Feign/RestTemplate/WebClient connect+read timeouts, Resilience4j TimeLimiter duration, Kafka request.timeout.ms/session.timeout.ms. | application*.yml under spring.datasource.hikari.*, feign.client.config.*, resilience4j.timelimiter.*, spring.kafka.*; RestTemplateBuilder/WebClient.Builder construction sites (flag any built with NO explicit timeout — infinite by default). | Layer name, key, value, unit, file:line. Explicitly flag any HTTP client built without a timeout. | Edge / timeout-chain-ordering scenarios; cross-referenced against infra-side ALB/NLB/API-GW timeouts in the Timeout Chain sheet.
Retry Amplification Inputs | For each outbound call in a chain, its retry count and backoff — used to compute worst-case multiplicative amplification across a multi-hop path. | Same annotations as Resilience Config, organized by caller→callee edges (derive edges from Feign client interfaces / RestTemplate call sites / method names matching known downstream services). | Caller, callee, retry count, backoff type. The consolidation script multiplies retry counts along a path — do not compute the product yourself in the scan; just report the edges. | App Resilience — retry-storm / self-inflicted-load scenarios.
Kafka Consumer / Producer Config | Per @KafkaListener or consumer factory: auto.offset.reset, enable.auto.commit (vs manual ack), max.poll.interval.ms vs realistic processing time, presence of an error handler / DLQ wiring, container-level concurrency. Per producer: acks, idempotence setting, retries. | @KafkaListener annotations and their consumer factory beans; application*.yml spring.kafka.consumer.*/producer.*; DefaultErrorHandler / SeekToCurrentErrorHandler / dead-letter-publishing-recoverer usage. | Listener method, topic, group id, each setting with file:line. Flag auto.offset.reset=latest on any consumer whose group appears durable/stateful (candidate for silent message loss). | Messaging/Kafka family — poison-message, duplicate-delivery, rebalance, and offset-loss scenarios.
Idempotency Evidence | For each event handler and file-ingestion write path: does the write show idempotency machinery (upsert / ON CONFLICT / merge, a dedup or processed-event-id table, natural-key uniqueness constraint) or a bare insert/save with no guard? | Repository/DAO save methods invoked from @KafkaListener or file-processing code paths; JPA @Table unique constraints; native SQL with ON CONFLICT/MERGE; any 'seen event id' check. | Handler name, evidence type found (or NONE_FOUND), file:line, a suspicion_level of low/medium/high (NONE_FOUND = high suspicion — cannot prove idempotency statically, only rank it). | Duplicate-delivery and pipeline-restart-idempotency scenarios — ranks which consumers to test first.
Anti-Pattern Sweep | Broad-catch exception swallowing around remote calls; unbounded thread pools / @Async without a bounded executor; hardcoded Thread.sleep in retry logic; HTTP clients built with no timeout (cross-ref with Timeout Chain); blocking calls inside a Kafka listener thread; multi-write event handlers without a transaction boundary. | grep/ripgrep for catch (Exception, catch (Throwable, Thread.sleep(, new RestTemplate() / WebClient.builder().build() with no timeout call chained, @Async without a named bounded executor bean, @KafkaListener methods calling blocking I/O without async offload. Semgrep rules are an optional accelerator if installable; otherwise pattern-match plus a read of the surrounding method for confirmation before flagging. | Pattern id, description, file:line, snippet, a plain-language severity_hint (not a formal score — that stays human judgment). | Generates candidate NEW scenarios beyond the current 90 — this category is expected to surface gaps, not just confirm existing ones.
Spring Profile Inventory | Every environment profile present (perf, prod, and any others) and every config file / config-file-per-profile that exists for it. | application.yml plus application-<profile>.yml per module; @Profile annotations in code; any profile-conditional @Bean. | Profile name, config file path(s), any profile-gated bean/behavior found in code (not just config). | Feeds the Profile Diff step below directly.
Profile Diff — perf vs prod
• For every config key found in the Spring Profile Inventory, resolve the EFFECTIVE value per profile (base application.yml overridden by application-<profile>.yml — do not stop at the base file).
• Diff perf vs prod key-by-key. Classify each difference as: expected (endpoints, hostnames, credential references, log levels) or suspicious (timeouts, pool sizes, retry counts, breaker thresholds, batch sizes, thread-pool sizes differing across environments — anything that changes SYSTEM BEHAVIOR, not just its target).
• A key present in one profile file and silently absent in the other is its own finding (missing_in_one) — do not assume it 'falls back to base' without confirming the override mechanism actually works that way for that key.
• Output feeds the Profile Mismatch Register sheet and directly resolves 'PERF Validity' flags already in the Scenario Catalog — a scenario marked Medium/Low PERF validity should point at the specific suspicious diff that causes the caveat.
Keeping this current
• New service repo added: run the full category list against it once at onboarding; add its row to the Service Inventory tab; propose new scenario IDs following the CE-<DOMAIN>-NN convention for any pattern not already covered.
• New dependency/library adopted (e.g., a new HTTP client, a new messaging library): add a row to this table before the next scan cycle — this table should grow with your stack, not silently miss new tech.
• Re-run cadence: re-scan after any change to resilience/timeout/Kafka config, and at minimum once per quarter to catch drift — config drift between scans is itself a finding worth tracking.

## Infra Scan Instructions
Infrastructure Scan — Method & Standard
Durable reference for discovering and cataloging cloud components from infrastructure-as-code repos, and for keeping the Service Inventory tab and the fault-domain taxonomy current as the architecture evolves. Tool-agnostic by design — detect the IaC tool in use per repo rather than assuming one.
Non-negotiable rules (same as the App tab)
• Every extracted fact carries evidence: {file path, line number / resource block, verbatim snippet}.
• Never assume a cloud-provider default for an unset attribute — record NOT_CONFIGURED and name the provider/resource-type default only if you can point to its source (provider docs version), otherwise leave it for human verification.
• A value set via a variable/module input that isn't resolvable without running the tool (terraform plan, cdk synth) is AMBIGUOUS with the variable name and every default/tfvars candidate recorded.
• Status vocabulary matches the App tab exactly: CONFIRMED ¦ NOT_FOUND ¦ NOT_CONFIGURED ¦ AMBIGUOUS ¦ EXTERNAL_CONFIG ¦ NOT_APPLICABLE.
Step 1 — Detect the IaC tool (per repo, do not assume)
Signal file(s) | Tool | Primary extraction approach
*.tf, *.tf.json, terraform.tfstate* | Terraform | Parse HCL resource blocks directly for CONFIRMED values; if `terraform` CLI is available, `terraform show -json` on a plan gives fully resolved values and should be preferred over static HCL parsing where variables are involved.
cdk.json + *.ts/*.py CDK constructs | AWS CDK | Static analysis of construct props is best-effort only — CDK constructs apply implicit defaults in code, not in the file you're reading. If `cdk synth` can be run, extract from the synthesized CloudFormation template instead for CONFIRMED-grade values.
template.yaml/json with AWSTemplateFormatVersion, or SAM's template.yaml | CloudFormation / SAM | Parse Resources: block directly — declarative, closest to ground truth without needing to execute anything.
serverless.yml | Serverless Framework | Parse provider:/functions:/resources: blocks; note this framework often layers its own defaults atop the CloudFormation it generates — flag accordingly.
None of the above found | Unknown / manual provisioning | Mark the repo NOT_APPLICABLE for automated extraction and log it in Open Items — infrastructure may be console/ClickOps-managed, which is itself a finding worth surfacing to leadership.
Step 2 — Component categories to extract
Component Category | Resource Types / Signals | What to Extract | Cross-Check Against | Feeds Fault Domain(s)
Compute | ECS Service + TaskDefinition (or equivalent: EKS, Lambda, EC2 ASG) | Launch type (Fargate/EC2), desired count, min/max healthy percent during deploy, CPU/memory, whether env vars override any app-side config (this is a common silent divergence from the checked-in application.yml). | App Scan census — flag any env-var override of a value the App scan also found in code, both values recorded. | Compute
Data store | RDS/Aurora cluster + instance, RDS Proxy, DynamoDB table | Engine + version, instance class, Multi-AZ, Aurora Global Database membership + failover priority/region roles, whether an RDS Proxy resource exists and which services' security groups/target groups point at it (this is how you CONFIRM the proxy-vs-direct split rather than inferring it from an app diagram). | Service Inventory tab's 'RDS Proxy' column — reconcile any disagreement rather than picking one source silently. | Data-Aurora / Data-<other>
Cache | ElastiCache replication group / cluster | Engine (Redis/Memcached), node type, Multi-AZ, number of shards/replicas, auth-token requirement, per-region vs shared cluster topology. | App Scan's client config for connection/auth patterns. | Cache
Messaging / broker | MSK cluster, self-managed broker security groups, or SaaS broker network path (VPC peering/PrivateLink to a message-broker SaaS) | Broker type, number of brokers/AZs, encryption-in-transit setting, auth mechanism (SASL/mTLS/IAM), network path (on-prem via Direct Connect vs in-VPC vs SaaS over PrivateLink). | App Scan's Kafka consumer/producer config category. | Messaging
Edge / ingress | ALB, NLB, API Gateway (REST or HTTP API), Route 53 records + routing policy | Idle timeout (ALB default 60s / commonly raised; NLB default varies), deregistration delay, API Gateway throttle burst/rate limit and integration timeout (hard cap on managed API Gateway), Route 53 routing policy (failover/latency/weighted) + TTL. | App Scan's Timeout Chain category — THIS is the piece that closes the loop between app-declared timeouts and the infra ceiling around them. | Edge / timeout-chain-ordering
Async / eventing | SQS queue + redrive policy/DLQ, EventBridge rule + schedule expression, SNS topic, Lambda function + concurrency/reserved-concurrency, S3 event notifications | Queue visibility timeout vs consumer processing time, DLQ maxReceiveCount, EventBridge schedule expression + target, Lambda reserved concurrency (a throttling ceiling that can silently cap a 'scheduled job' pattern). | App Scan's scheduled-job findings (duplicate/missed execution risk) — infra concurrency limits are often the actual root cause. | Compute (scheduled) / Pipeline
Secrets & config | Secrets Manager secret, SSM Parameter Store parameter, KMS key + key policy | Rotation configuration (automatic vs none), which IAM roles/policies grant access, KMS key policy grantees, whether a parameter uses SecureString. | App Scan's EXTERNAL_CONFIG-flagged keys — this is where those get their access-pattern facts filled in (not their values). | Config/Secrets
Network boundary | VPC endpoints (Interface/Gateway), Direct Connect / Transit Gateway attachments, security groups on cross-boundary paths | Which AWS services have a private endpoint vs traverse NAT/public path; on-prem-bound routes and what depends on them. | App Scan's on-prem/external-dependency findings. | Network
DR / region posture | Aurora Global Database region config, Route 53 failover records, any DR-orchestration resource (state machine, custom automation, alarm-triggered Lambda/pipeline) | Per-service DR posture as CONFIRMED infra fact (active/active, active/passive, N-active, pilot light) rather than as previously diagrammed/reported — infra is ground truth here. | Service Inventory tab's DR Posture column — reconcile disagreements explicitly. | Region/DR
Step 3 — Reconciling infra facts against the Service Inventory tab
• The Service Inventory tab was originally built from architecture diagrams — treat infra-as-code as the higher-confidence source when the two disagree, but record BOTH values and the disagreement rather than silently overwriting the diagram-derived one.
• Any component found in infra that has no corresponding row/mention in Service Inventory is a coverage gap — add it rather than dropping it.
• RDS Proxy presence/absence is the single highest-value reconciliation in this pass — several catalog scenarios (e.g., writer-failover asymmetry) depend on it being correct.
Onboarding a new AWS component or service (future-proofing)
• 1. Add a row to the Step-2 table above: component category, resource types/signals, what to extract, what to cross-check.
• 2. Decide which existing Fault Domain (Coverage Matrix tab in the main workbook) it belongs to, or declare a new one if genuinely novel.
• 3. Draft at least one new scenario using the existing ID convention: CE-<DOMAIN>-NN, with the same required fields as the Scenario Catalog tab (hypothesis, tooling, blast radius, abort condition, dual success criteria, PERF validity).
• 4. Add the component to the Service Inventory tab for every service that adopts it, not just the first one.